Texas Education Day 2024 Call

Date: 3/1/2024
Location: TEAMS

Agenda

Registration Updates

- 161 Registered (up 81 from last Friday)

- $31,477.00 Collected

  - BTN Panel, Suzanne Neufang, etc. registered

  - Follow up with Karen on RL

Program Updates

- BTN Panel (Cindy)

  - Will Tate has setup pre-call with all panelists for April

- DFW Airport/Ken Buchanan (Cindy)

  - Setup call with Dean next week

- Lunch – Suzanne Neufang/Dave Harvey (Cindy)

- Removed Rafael from lineup due to no responses

- Breakouts (Education/Karen)

  - Mental Health/Out of Office – Gloria’s Team

    - No updates

  - Emerging Technologies in Cyber Securities – Frank Harrison, WTP

    - Meredith to follow up on hotel

    - Meredith to send out the presentation

  - Sustainability with Delta Air Lines

    - Houston Travel Manager

      - Gina Flynn, Shell (Meredith to follow up)

- Keynote (Karen)

  - Signed and invoices received

- All presentation need to be in GBTA/DFW Slide Format (except Keynote)

Budget Updates

- Current Expense Total: $12,391.06

- Keynote and Books are being processed – budgeting $7,000 total

  - Books $4,319.18 (paid)

  - Keynote Speaker Fee $1,500

  - T&E $2,000

AV Updates

- Moving forward with Inside Image Design (thank you Bryan!)

  - $14,044.72

- WiFi through hotel

F&B Updates

- Stacey/Jake/Karen to met with hotel last Friday

- Waiting on hotel to send menu options and per person pricing so we can edit

Hotel Room Block Updates

- Block cutoff date was extended to end of March by hotel. On pace to fill block.

- Need rooming list for speakers (Jake)

Reservations for Speakers

- Jake to handle any reservations for Air/Hotel for speakers who cannot cover their own expenses. Expectation is for most to cover a portion but we can accommodate if needed.

- We will apply any comps we receive towards speakers.

- Ground Transportation for Speakers will be covered by Freedom Charters

Sponsor Updates

- $73,700 Committed

- $44,750 Paid + Tickets from SWA

- New Sponsors

  - Charging Station and Enterprise – Invoiced

  - Sustainability/Water Bottle – Qatar Airways – Invoiced

  - Jake working on pricing for Carbon Offset purchases and reaching out to Visit Frisco to see if they’ll cover cost.