Texas Education Day 2024 Call
Date: 3/15/2024
Location: TEAMS
Agenda
Registration Updates
· 204 Registered (up 8 from last Friday)
· $35,403.00 Collected
Program Updates
· BTN Panel (Cindy)
· Will Tate has setup pre-call with all panelists for April 5th
· Will to ask panelists if they will stay for event
· Jeff Klee, Doreen Burse, Suzanne Neufang are not staying for remainder of event on Friday
· DFW Airport/Ken Buchanan (Cindy)
· “A Traveler’s Sustainable Journey through DFW Airport”
· Lunch – Suzanne Neufang/Dave Harvey (Cindy)
· Prep Call April 4th 
· Breakouts (Education/Karen)
· “Out of Office: Give Yourself Permission for Travel Wellness”
· Gloria Gonzalez, Stacie Prusha, Ana Lenis, Joseph Metallo
· They have GBTA template and have converted slides
· “Emerging Technologies in Cyber Securities”
· Frank Harrison, WTP
· Prep call scheduled 3/21
· Sustainability with Delta Air Lines
· “The Ripple Effect of Sustainability”
· No TM from Houston – should we stick with 3 total TMs?
· Cindy will reach out to Trish for last shot for Houston
· TMs we’ve solicited: Nikki Leads (HP), Holly/Halliburton, Adam/HP Inc, Kim Bilsky 
· Prep call scheduled 4/4
· Keynote (Karen)
· “How to Tell a Story” 
· Kate Teller
GTP/CEU Credits and Submission to GBTA – follow up Meredith/Candace
All presentation need to be in GBTA/DFW Slide Format (except Keynote)
Budget Updates
· Current Expense Total: $12,871.06
· Keynote and Books are being processed – budgeting $7,000 total
· Books $4,319.18 (paid)
· Keynote Speaker Fee $1,500
· T&E $1,000 *using SWA Ticket for Airfare
AV Updates
· Moving forward with Inside Image Design (thank you Bryan!)
· $14,044.72 (confirmed)
· 50% deposit due at contract (7030.66)
· WiFi through hotel
· Confirming with Encore
F&B Updates
· Hovering at $200pp ++ but working on edits with hotel
· We will send an email 4/4 to ask attendee list who will be attending reception, flight time, etc. 
Hotel Room Block Updates
	
	4/17
	4/18
	4/19

	Contracted
	
	125
	

	Picked Up
	5
	105
	6


· Block cutoff date was extended to end 3/22
· Need rooming list for speakers (Jake)*
· Rooms have been sent, will send any last minute to Karen 
· Post cutoff plan with hotel
· Link for % off
· Sheraton 
· La Monica has provided a code
Sponsor Updates
· $73,700 Committed
· $51,500 Paid + Tickets from SWA
· Friday Photo Booth – working on pricing
· KWT First Right
· Carbon Offset Sponsorship
· $1,500 Sponsorship
· Jake/La Monica to send email to Christina Decker/Visit Frisco
· Luggage Storage Room Sponsorship
· Jake to follow up on luggage storage room and dedicated staff member
· Speaker Ready Room Sponsorship
· Bottled Water/Snacks
Transportation
· Jake to send information to Cindy to forward out to the other chapter President’s 
· Charter Bus deadline – April 1st
· Airport Transfer deadline – April 5th 


*Request has come from a few sponsors to have their logo listed in Agenda. Working on including that in the current agenda online. Suggesting not to list on the actual registration page as it will slow the page down and break links.  

