Texas Education Day 2024 Call

Date: 3/8/2024
Location: TEAMS

Agenda

Registration Updates

- 196 Registered (up 35 from last Friday)

- $33,687.00 Collected

  - BTN Panel, Suzanne Neufang, etc. are registered

    - Will Tate?

Program Updates

- BTN Panel (Cindy)

  - Will Tate has setup pre-call with all panelists for April

  - Will to ask panelists if they will stay for event

- DFW Airport/Ken Buchanan (Cindy)

  - Call with Dean this week (Cindy/Stacey)

  - “A Traveler’s Sustainable Journey through DFW Airport”

- Lunch – Suzanne Neufang/Dave Harvey (Cindy)

- Breakouts (Education/Karen)

  - Mental Health/Out of Office – Gloria’s Team

    - No updates – Karen to follow up on name

  - Emerging Technologies in Cyber Securities – Frank Harrison, WTP

    - Meredith to sent out the presentation

  - Sustainability with Delta Air Lines

    - Name of breakout – update based on DFWs?

- Keynote (Karen)

  - “How to Tell a Story” title

GTP/CEU Credits and Submission to GBTA

All presentation need to be in GBTA/DFW Slide Format (except Keynote)

Budget Updates

- Current Expense Total: $12,871.06

- Keynote and Books are being processed – budgeting $7,000 total

  - Books $4,319.18 (paid)

  - Keynote Speaker Fee $1,500

  - T&E $2,000 *using SWA Ticket for Airfare

AV Updates

- Moving forward with Inside Image Design (thank you Bryan!)

  - $14,044.72 Confirm

- WiFi through hotel

  - Confirm with Encore

- List of sponsors with banners to Karen

F&B Updates

- Received per person budget with totals but numbers are off. Call this afternoon with hotel.

Hotel Room Block Updates

- Block cutoff date was extended to end of March by hotel. On pace to fill block.

- Need rooming list for speakers (Jake)*

- Post cutoff plan with hotel

Reservations for Speakers

- Jake to handle any reservations for Air/Hotel for speakers who cannot cover their own expenses. Expectation is for most to cover a portion but we can accommodate if needed.

- We will apply any comps we receive towards speakers.

- Ground Transportation for Speakers will be covered by Freedom Charters

Sponsor Updates

- $73,700 Committed

- $45,500 Paid + Tickets from SWA

- New Sponsors

- Follow up with Bryan on Roaming Photo Booth for Reception

  - Ask United for sponsors referral for Photo Booth at Reception

  - Cindy to ask John

- Photography/Videography

*Request has come from a few sponsors to have their logo listed in Agenda. Working on including that in the current agenda online. Suggesting not to list on the actual registration page as it will slow the page down and break links.

*Email 2 weeks out to attendees to see if they will attending reception, flight time, etc.

*Rooms Chapter are covering